## REI - Smoke Test
Scenarios - REI | Difference | HELO2 - Staging Link | 2024-06-20 | 2024-06-18 | 2024-06-17
Blank Shipment Issuer (No Null Values) | 0 | https://helo-frontend-staging-react.azurewebsites.net/containers?viewState=%7B%22queries%22%3A%5B%7B%22queryId%22%3A%22containers_v2%22%2C%22queryName%22%3A%22containers_v2%22%2C%22filters%22%3A%5B%7B%22columnId%22%3A%22issuedBy%22%2C%22operator%22%3A%22AND%22%2C%22condition%22%3A%22blank%22%2C%22filterValueType%22%3A%22text%22%7D%5D%2C%22sort%22%3A%5B%5D%7D%5D%7D | 0 | 0 | 0
Blank Status Containers | 0 | https://helo-frontend-staging-react.azurewebsites.net/containers?viewState=%7B%22queries%22%3A%5B%7B%22queryId%22%3A%22containers_v2%22%2C%22queryName%22%3A%22containers_v2%22%2C%22filters%22%3A%5B%7B%22columnId%22%3A%22heloItineraryStatus%22%2C%22operator%22%3A%22AND%22%2C%22condition%22%3A%22blank%22%2C%22filterValueType%22%3A%22text%22%7D%5D%2C%22sort%22%3A%5B%5D%7D%5D%7D | 0 | 0 | 0
Blank Status Containers (ETA > 5/1/24) | 0 | https://helo-frontend-staging-react.azurewebsites.net/containers?viewState=%7B%22queries%22%3A%5B%7B%22queryId%22%3A%22containers_v2%22%2C%22queryName%22%3A%22containers_v2%22%2C%22filters%22%3A%5B%7B%22columnId%22%3A%22etaShipmentDestination%22%2C%22operator%22%3A%22OR%22%2C%22filterValueType%22%3A%22date%22%2C%22operand1%22%3A%7B%22condition%22%3A%22greaterThan%22%2C%22filterValue%22%3A%222024-05-01+00%3A00%3A00%22%2C%22filterValueType%22%3A%22date%22%7D%2C%22operand2%22%3A%7B%22condition%22%3A%22blank%22%2C%22filterValueType%22%3A%22date%22%7D%7D%2C%7B%22columnId%22%3A%22heloItineraryStatus%22%2C%22operator%22%3A%22AND%22%2C%22condition%22%3A%22blank%22%2C%22filterValueType%22%3A%22text%22%7D%5D%2C%22sort%22%3A%5B%7B%22columnId%22%3A%22etaShipmentDestination%22%2C%22sortDirection%22%3A%22descending%22%7D%5D%7D%5D%7D | 0 | 0 | 0
Days in Status < 0 | 0 | https://helo-frontend-staging-react.azurewebsites.net/containers?viewState=%7B%22queries%22%3A%5B%7B%22queryId%22%3A%22containers_v2%22%2C%22queryName%22%3A%22containers_v2%22%2C%22filters%22%3A%5B%7B%22columnId%22%3A%22daysInStatus%22%2C%22operator%22%3A%22AND%22%2C%22condition%22%3A%22lessThan%22%2C%22filterValue%22%3A0%2C%22filterValueType%22%3A%22number%22%7D%5D%2C%22sort%22%3A%5B%7B%22columnId%22%3A%22etaPortUnlading%22%2C%22sortDirection%22%3A%22descending%22%7D%5D%7D%5D%7D | 0 | 0 | 0
Blank Latest Vessel (On Water or on Vessel) (ETA > 5/1/24) | 0 | https://helo-frontend-staging-react.azurewebsites.net/containers?viewState=%7B%22queries%22%3A%5B%7B%22queryId%22%3A%22containers_v2%22%2C%22queryName%22%3A%22containers_v2%22%2C%22filters%22%3A%5B%7B%22columnId%22%3A%22vessel%22%2C%22operator%22%3A%22AND%22%2C%22condition%22%3A%22blank%22%2C%22filterValueType%22%3A%22text%22%7D%2C%7B%22columnId%22%3A%22etaPortUnlading%22%2C%22operator%22%3A%22OR%22%2C%22filterValueType%22%3A%22date%22%2C%22operand1%22%3A%7B%22condition%22%3A%22greaterThan%22%2C%22filterValue%22%3A%222024-05-01+00%3A00%3A00%22%2C%22filterValueType%22%3A%22date%22%7D%2C%22operand2%22%3A%7B%22condition%22%3A%22blank%22%2C%22filterValueType%22%3A%22date%22%7D%7D%2C%7B%22columnId%22%3A%22heloItineraryStatus%22%2C%22operator%22%3A%22OR%22%2C%22filterValueType%22%3A%22text%22%2C%22operand1%22%3A%7B%22condition%22%3A%22contains%22%2C%22filterValue%22%3A%22on+water%22%2C%22filterValueType%22%3A%22text%22%7D%2C%22operand2%22%3A%7B%22condition%22%3A%22contains%22%2C%22filterValue%22%3A%22on+vessel%22%2C%22filterValueType%22%3A%22text%22%7D%7D%5D%2C%22sort%22%3A%5B%7B%22columnId%22%3A%22etaPortUnlading%22%2C%22sortDirection%22%3A%22descending%22%7D%5D%7D%5D%7D | 0 | 0 | 0
Blank PTA Unlading Port (On Water or On Vessel) | 5 | https://helo-frontend-staging-react.azurewebsites.net/containers?viewState=%7B%22queries%22%3A%5B%7B%22queryId%22%3A%22containers_v2%22%2C%22queryName%22%3A%22containers_v2%22%2C%22filters%22%3A%5B%7B%22columnId%22%3A%22heloItineraryStatus%22%2C%22operator%22%3A%22OR%22%2C%22filterValueType%22%3A%22text%22%2C%22operand1%22%3A%7B%22condition%22%3A%22contains%22%2C%22filterValue%22%3A%22on+water%22%2C%22filterValueType%22%3A%22text%22%7D%2C%22operand2%22%3A%7B%22condition%22%3A%22contains%22%2C%22filterValue%22%3A%22on+vessel%22%2C%22filterValueType%22%3A%22text%22%7D%7D%2C%7B%22columnId%22%3A%22ptaPortUnlading%22%2C%22operator%22%3A%22AND%22%2C%22condition%22%3A%22blank%22%2C%22filterValueType%22%3A%22date%22%7D%5D%2C%22sort%22%3A%5B%5D%7D%5D%7D | 14 | 9 | 9
Blank PTA Unlading Port (On Water or On Vessel) Status > 5/1/24 | 5 | https://helo-frontend-staging-react.azurewebsites.net/containers?viewState=%7B%22queries%22%3A%5B%7B%22queryId%22%3A%22containers_v2%22%2C%22queryName%22%3A%22containers_v2%22%2C%22filters%22%3A%5B%7B%22columnId%22%3A%22ptaPortUnlading%22%2C%22operator%22%3A%22AND%22%2C%22condition%22%3A%22blank%22%2C%22filterValueType%22%3A%22date%22%7D%2C%7B%22columnId%22%3A%22statusDate%22%2C%22operator%22%3A%22OR%22%2C%22filterValueType%22%3A%22date%22%2C%22operand1%22%3A%7B%22condition%22%3A%22greaterThan%22%2C%22filterValue%22%3A%222024-05-01+00%3A00%3A00%22%2C%22filterValueType%22%3A%22date%22%7D%2C%22operand2%22%3A%7B%22condition%22%3A%22blank%22%2C%22filterValueType%22%3A%22date%22%7D%7D%2C%7B%22columnId%22%3A%22heloItineraryStatus%22%2C%22operator%22%3A%22OR%22%2C%22filterValueType%22%3A%22text%22%2C%22operand1%22%3A%7B%22condition%22%3A%22contains%22%2C%22filterValue%22%3A%22on+water%22%2C%22filterValueType%22%3A%22text%22%7D%2C%22operand2%22%3A%7B%22condition%22%3A%22contains%22%2C%22filterValue%22%3A%22on+vessel%22%2C%22filterValueType%22%3A%22text%22%7D%7D%5D%2C%22sort%22%3A%5B%7B%22columnId%22%3A%22statusDate%22%2C%22sortDirection%22%3A%22descending%22%7D%5D%7D%5D%7D | 14 | 9 | 9
Blank Free Time Expires, discharged and later | - | - | - | - | -
Blank Free Time Expires, discharged and undelivered | - | - | - | - | -
Blank PTA Delivery Location | - | - | - | - | -
Blank Arrival Shipment Destination | 14 | https://helo-frontend-staging-react.azurewebsites.net/containers?viewState=%7B%22queries%22%3A%5B%7B%22queryId%22%3A%22containers_v2%22%2C%22queryName%22%3A%22containers_v2%22%2C%22filters%22%3A%5B%7B%22columnId%22%3A%22itineraryStatus%22%2C%22operator%22%3A%22AND%22%2C%22condition%22%3A%22in%22%2C%22filterValue%22%3A%22Actual+Time+of+Arrival%2CActual+Time+of+Arrival+%28POD%29%2CActual+Time+of+Arrival+%28POU%29%2CActual+Time+of+Vessel+Arrival+at+Destination+Port%22%2C%22filterValueType%22%3A%22text%22%7D%2C%7B%22columnId%22%3A%22arrivalShipmentDestination%22%2C%22operator%22%3A%22AND%22%2C%22condition%22%3A%22blank%22%2C%22filterValueType%22%3A%22date%22%7D%5D%2C%22sort%22%3A%5B%5D%7D%5D%7D | 37 | 23 | 23
Blank Arrival Shipment Destination - Status > 5/1/24 | 14 | https://helo-frontend-staging-react.azurewebsites.net/containers?viewState=%7B%22queries%22%3A%5B%7B%22queryId%22%3A%22containers_v2%22%2C%22queryName%22%3A%22containers_v2%22%2C%22filters%22%3A%5B%7B%22columnId%22%3A%22itineraryStatus%22%2C%22operator%22%3A%22AND%22%2C%22condition%22%3A%22in%22%2C%22filterValue%22%3A%22Actual+Time+of+Arrival%2CActual+Time+of+Arrival+%28POD%29%2CActual+Time+of+Arrival+%28POU%29%2CActual+Time+of+Vessel+Arrival+at+Destination+Port%22%2C%22filterValueType%22%3A%22text%22%7D%2C%7B%22columnId%22%3A%22arrivalShipmentDestination%22%2C%22operator%22%3A%22AND%22%2C%22condition%22%3A%22blank%22%2C%22filterValueType%22%3A%22date%22%7D%2C%7B%22columnId%22%3A%22statusDate%22%2C%22operator%22%3A%22OR%22%2C%22filterValueType%22%3A%22date%22%2C%22operand1%22%3A%7B%22condition%22%3A%22greaterThan%22%2C%22filterValue%22%3A%222024-05-01+00%3A00%3A00%22%2C%22filterValueType%22%3A%22date%22%7D%2C%22operand2%22%3A%7B%22condition%22%3A%22blank%22%2C%22filterValueType%22%3A%22date%22%7D%7D%5D%2C%22sort%22%3A%5B%7B%22columnId%22%3A%22statusDate%22%2C%22sortDirection%22%3A%22descending%22%7D%5D%7D%5D%7D | 37 | 23 | 23
Containers | - | - | - | - | -
Days in Status > 50 (not complete) | 0 | https://helo-frontend-staging-react.azurewebsites.net/containers?viewState=%7B%22queries%22%3A%5B%7B%22queryId%22%3A%22containers_v2%22%2C%22queryName%22%3A%22containers_v2%22%2C%22filters%22%3A%5B%7B%22columnId%22%3A%22daysInStatus%22%2C%22operator%22%3A%22AND%22%2C%22condition%22%3A%22greaterThan%22%2C%22filterValue%22%3A50%2C%22filterValueType%22%3A%22number%22%7D%2C%7B%22columnId%22%3A%22heloItineraryStatus%22%2C%22operator%22%3A%22AND%22%2C%22condition%22%3A%22notContains%22%2C%22filterValue%22%3A%22completed%22%2C%22filterValueType%22%3A%22text%22%7D%5D%2C%22sort%22%3A%5B%7B%22columnId%22%3A%22heloItineraryStatus%22%2C%22sortDirection%22%3A%22descending%22%7D%5D%7D%5D%7D | 0 | 0 | 0
At Origin Port > 10 days | 0 | https://helo-frontend-staging-react.azurewebsites.net/containers?viewState=%7B%22queries%22%3A%5B%7B%22queryId%22%3A%22containers_v2%22%2C%22queryName%22%3A%22containers_v2%22%2C%22filters%22%3A%5B%7B%22columnId%22%3A%22heloItineraryStatus%22%2C%22operator%22%3A%22AND%22%2C%22condition%22%3A%22contains%22%2C%22filterValue%22%3A%22at+Origin+Port%22%2C%22filterValueType%22%3A%22text%22%7D%2C%7B%22columnId%22%3A%22daysInStatus%22%2C%22operator%22%3A%22AND%22%2C%22condition%22%3A%22greaterThan%22%2C%22filterValue%22%3A10%2C%22filterValueType%22%3A%22number%22%7D%5D%2C%22sort%22%3A%5B%5D%7D%5D%7D | 0 | 0 | 0
On Water > 15 days | 0 | https://helo-frontend-staging-react.azurewebsites.net/containers?viewState=%7B%22queries%22%3A%5B%7B%22queryId%22%3A%22containers_v2%22%2C%22queryName%22%3A%22containers_v2%22%2C%22filters%22%3A%5B%7B%22columnId%22%3A%22heloItineraryStatus%22%2C%22operator%22%3A%22AND%22%2C%22condition%22%3A%22contains%22%2C%22filterValue%22%3A%22On+Water%22%2C%22filterValueType%22%3A%22text%22%7D%2C%7B%22columnId%22%3A%22daysInStatus%22%2C%22operator%22%3A%22AND%22%2C%22condition%22%3A%22greaterThan%22%2C%22filterValue%22%3A15%2C%22filterValueType%22%3A%22number%22%7D%5D%2C%22sort%22%3A%5B%5D%7D%5D%7D | 7 | 7 | 7
At Transshipment Port > 7 days | 0 | https://helo-frontend-staging-react.azurewebsites.net/containers?viewState=%7B%22queries%22%3A%5B%7B%22queryId%22%3A%22containers_v2%22%2C%22queryName%22%3A%22containers_v2%22%2C%22filters%22%3A%5B%7B%22columnId%22%3A%22heloItineraryStatus%22%2C%22operator%22%3A%22AND%22%2C%22condition%22%3A%22contains%22%2C%22filterValue%22%3A%22At+Transshipment+Port%22%2C%22filterValueType%22%3A%22text%22%7D%2C%7B%22columnId%22%3A%22daysInStatus%22%2C%22operator%22%3A%22AND%22%2C%22condition%22%3A%22greaterThan%22%2C%22filterValue%22%3A7%2C%22filterValueType%22%3A%22number%22%7D%5D%2C%22sort%22%3A%5B%5D%7D%5D%7D | 0 | 0 | 0
At Port of Unlading > 5 days | 0 | https://helo-frontend-staging-react.azurewebsites.net/containers?viewState=%7B%22queries%22%3A%5B%7B%22queryId%22%3A%22containers_v2%22%2C%22queryName%22%3A%22containers_v2%22%2C%22filters%22%3A%5B%7B%22columnId%22%3A%22daysInStatus%22%2C%22operator%22%3A%22AND%22%2C%22condition%22%3A%22greaterThan%22%2C%22filterValue%22%3A5%2C%22filterValueType%22%3A%22number%22%7D%2C%7B%22columnId%22%3A%22heloItineraryStatus%22%2C%22operator%22%3A%22AND%22%2C%22condition%22%3A%22contains%22%2C%22filterValue%22%3A%22at+port+of+Unlading%22%2C%22filterValueType%22%3A%22text%22%7D%5D%2C%22sort%22%3A%5B%5D%7D%5D%7D | 0 | 0 | 0
At Port of Unlading > 5 days - Status Date > 5/1/24 | 0 | https://helo-frontend-staging-react.azurewebsites.net/containers?viewState=%7B%22queries%22%3A%5B%7B%22queryId%22%3A%22containers_v2%22%2C%22queryName%22%3A%22containers_v2%22%2C%22filters%22%3A%5B%7B%22columnId%22%3A%22daysInStatus%22%2C%22operator%22%3A%22AND%22%2C%22condition%22%3A%22greaterThan%22%2C%22filterValue%22%3A5%2C%22filterValueType%22%3A%22number%22%7D%2C%7B%22columnId%22%3A%22statusDate%22%2C%22operator%22%3A%22OR%22%2C%22filterValueType%22%3A%22date%22%2C%22operand1%22%3A%7B%22condition%22%3A%22greaterThan%22%2C%22filterValue%22%3A%222024-05-01+00%3A00%3A00%22%2C%22filterValueType%22%3A%22date%22%7D%2C%22operand2%22%3A%7B%22condition%22%3A%22blank%22%2C%22filterValueType%22%3A%22date%22%7D%7D%2C%7B%22columnId%22%3A%22heloItineraryStatus%22%2C%22operator%22%3A%22AND%22%2C%22condition%22%3A%22contains%22%2C%22filterValue%22%3A%22at+port+of+unlading%22%2C%22filterValueType%22%3A%22text%22%7D%5D%2C%22sort%22%3A%5B%5D%7D%5D%7D | 0 | 0 | 0
At Port of Unlading > 15 days | 0 | https://helo-frontend-staging-react.azurewebsites.net/containers?viewState=%7B%22queries%22%3A%5B%7B%22queryId%22%3A%22containers_v2%22%2C%22queryName%22%3A%22containers_v2%22%2C%22filters%22%3A%5B%7B%22columnId%22%3A%22daysInStatus%22%2C%22operator%22%3A%22AND%22%2C%22condition%22%3A%22greaterThan%22%2C%22filterValue%22%3A15%2C%22filterValueType%22%3A%22number%22%7D%2C%7B%22columnId%22%3A%22heloItineraryStatus%22%2C%22operator%22%3A%22AND%22%2C%22condition%22%3A%22contains%22%2C%22filterValue%22%3A%22at+port+of+Unlading%22%2C%22filterValueType%22%3A%22text%22%7D%5D%2C%22sort%22%3A%5B%7B%22columnId%22%3A%22daysInStatus%22%2C%22sortDirection%22%3A%22ascending%22%7D%5D%7D%5D%7D | 0 | 0 | 0
At Port of Unlading > 15 days - Status Date > 5/1/24 | 0 | https://helo-frontend-staging-react.azurewebsites.net/containers?viewState=%7B%22queries%22%3A%5B%7B%22queryId%22%3A%22containers_v2%22%2C%22queryName%22%3A%22containers_v2%22%2C%22filters%22%3A%5B%7B%22columnId%22%3A%22daysInStatus%22%2C%22operator%22%3A%22AND%22%2C%22condition%22%3A%22greaterThan%22%2C%22filterValue%22%3A15%2C%22filterValueType%22%3A%22number%22%7D%2C%7B%22columnId%22%3A%22statusDate%22%2C%22operator%22%3A%22OR%22%2C%22filterValueType%22%3A%22date%22%2C%22operand1%22%3A%7B%22condition%22%3A%22greaterThan%22%2C%22filterValue%22%3A%222024-05-01+00%3A00%3A00%22%2C%22filterValueType%22%3A%22date%22%7D%2C%22operand2%22%3A%7B%22condition%22%3A%22blank%22%2C%22filterValueType%22%3A%22date%22%7D%7D%2C%7B%22columnId%22%3A%22heloItineraryStatus%22%2C%22operator%22%3A%22AND%22%2C%22condition%22%3A%22contains%22%2C%22filterValue%22%3A%22at+port+of+unlading%22%2C%22filterValueType%22%3A%22text%22%7D%5D%2C%22sort%22%3A%5B%5D%7D%5D%7D | 0 | 0 | 0
Arrived and Available > 5 days | 0 | https://helo-frontend-staging-react.azurewebsites.net/containers?viewState=%7B%22queries%22%3A%5B%7B%22queryId%22%3A%22containers_v2%22%2C%22queryName%22%3A%22containers_v2%22%2C%22filters%22%3A%5B%7B%22columnId%22%3A%22daysInStatus%22%2C%22operator%22%3A%22AND%22%2C%22condition%22%3A%22greaterThan%22%2C%22filterValue%22%3A5%2C%22filterValueType%22%3A%22number%22%7D%2C%7B%22columnId%22%3A%22heloItineraryStatus%22%2C%22operator%22%3A%22AND%22%2C%22condition%22%3A%22contains%22%2C%22filterValue%22%3A%22Arrived+and+Available%22%2C%22filterValueType%22%3A%22text%22%7D%5D%2C%22sort%22%3A%5B%5D%7D%5D%7D | 0 | 0 | 0
At Final Destination > 20 days | 0 | https://helo-frontend-staging-react.azurewebsites.net/containers?viewState=%7B%22queries%22%3A%5B%7B%22queryId%22%3A%22containers_v2%22%2C%22queryName%22%3A%22containers_v2%22%2C%22filters%22%3A%5B%7B%22columnId%22%3A%22daysInStatus%22%2C%22operator%22%3A%22AND%22%2C%22condition%22%3A%22greaterThan%22%2C%22filterValue%22%3A20%2C%22filterValueType%22%3A%22number%22%7D%2C%7B%22columnId%22%3A%22heloItineraryStatus%22%2C%22operator%22%3A%22AND%22%2C%22condition%22%3A%22in%22%2C%22filterValue%22%3A%22At+Final+Destination%22%2C%22filterValueType%22%3A%22text%22%7D%5D%2C%22sort%22%3A%5B%5D%7D%5D%7D | 3 | 3 | 3
Container Ready Empty > 15 days | 0 | https://helo-frontend-staging-react.azurewebsites.net/containers?viewState=%7B%22queries%22%3A%5B%7B%22queryId%22%3A%22containers_v2%22%2C%22queryName%22%3A%22containers_v2%22%2C%22filters%22%3A%5B%7B%22columnId%22%3A%22daysInStatus%22%2C%22operator%22%3A%22AND%22%2C%22condition%22%3A%22greaterThan%22%2C%22filterValue%22%3A15%2C%22filterValueType%22%3A%22number%22%7D%2C%7B%22columnId%22%3A%22heloItineraryStatus%22%2C%22operator%22%3A%22AND%22%2C%22condition%22%3A%22contains%22%2C%22filterValue%22%3A%22Container+Ready+Empty%22%2C%22filterValueType%22%3A%22text%22%7D%5D%2C%22sort%22%3A%5B%5D%7D%5D%7D | 0 | 0 | 0
Empty Shipment Origin (Status Date > 5/1/24) | 0 | https://helo-frontend-staging-react.azurewebsites.net/containers?viewState=%7B%22queries%22%3A%5B%7B%22queryId%22%3A%22containers_v2%22%2C%22queryName%22%3A%22containers_v2%22%2C%22filters%22%3A%5B%7B%22columnId%22%3A%22shipmentOrigin%22%2C%22operator%22%3A%22AND%22%2C%22condition%22%3A%22blank%22%2C%22filterValueType%22%3A%22text%22%7D%2C%7B%22columnId%22%3A%22statusDate%22%2C%22operator%22%3A%22OR%22%2C%22filterValueType%22%3A%22date%22%2C%22operand1%22%3A%7B%22condition%22%3A%22blank%22%2C%22filterValueType%22%3A%22date%22%7D%2C%22operand2%22%3A%7B%22condition%22%3A%22greaterThan%22%2C%22filterValue%22%3A%222024-05-01+00%3A00%3A00%22%2C%22filterValueType%22%3A%22date%22%7D%7D%5D%2C%22sort%22%3A%5B%5D%7D%5D%7D | 0 | 0 | 0
Empty Port of Unlading, | 0 | https://helo-frontend-staging-react.azurewebsites.net/containers?viewState=%7B%22queries%22%3A%5B%7B%22queryId%22%3A%22containers_v2%22%2C%22queryName%22%3A%22containers_v2%22%2C%22filters%22%3A%5B%7B%22columnId%22%3A%22unladingPort%22%2C%22operator%22%3A%22AND%22%2C%22condition%22%3A%22blank%22%2C%22filterValueType%22%3A%22text%22%7D%5D%2C%22sort%22%3A%5B%5D%7D%5D%7D | 0 | 0 | 0
Empty BL Destination | - | - | - | - | -
Empty Shipment Destination (Status Date > 5/1/24) | 0 | https://helo-frontend-staging-react.azurewebsites.net/containers?viewState=%7B%22queries%22%3A%5B%7B%22queryId%22%3A%22containers_v2%22%2C%22queryName%22%3A%22containers_v2%22%2C%22filters%22%3A%5B%7B%22columnId%22%3A%22shipmentDestination%22%2C%22operator%22%3A%22AND%22%2C%22condition%22%3A%22blank%22%2C%22filterValueType%22%3A%22text%22%7D%2C%7B%22columnId%22%3A%22statusDate%22%2C%22operator%22%3A%22OR%22%2C%22filterValueType%22%3A%22date%22%2C%22operand1%22%3A%7B%22condition%22%3A%22blank%22%2C%22filterValueType%22%3A%22date%22%7D%2C%22operand2%22%3A%7B%22condition%22%3A%22greaterThan%22%2C%22filterValue%22%3A%222024-05-01+00%3A00%3A00%22%2C%22filterValueType%22%3A%22date%22%7D%7D%5D%2C%22sort%22%3A%5B%5D%7D%5D%7D | 0 | 0 | 0
Empty Carrier (Status Date > 5/1/24) | 1 | https://helo-frontend-staging-react.azurewebsites.net/containers?viewState=%7B%22queries%22%3A%5B%7B%22queryId%22%3A%22containers_v2%22%2C%22queryName%22%3A%22containers_v2%22%2C%22filters%22%3A%5B%7B%22columnId%22%3A%22carrier%22%2C%22operator%22%3A%22AND%22%2C%22condition%22%3A%22blank%22%2C%22filterValueType%22%3A%22text%22%7D%2C%7B%22columnId%22%3A%22statusDate%22%2C%22operator%22%3A%22OR%22%2C%22filterValueType%22%3A%22date%22%2C%22operand1%22%3A%7B%22condition%22%3A%22blank%22%2C%22filterValueType%22%3A%22date%22%7D%2C%22operand2%22%3A%7B%22condition%22%3A%22greaterThan%22%2C%22filterValue%22%3A%222024-05-01+00%3A00%3A00%22%2C%22filterValueType%22%3A%22date%22%7D%7D%5D%2C%22sort%22%3A%5B%7B%22columnId%22%3A%22statusDate%22%2C%22sortDirection%22%3A%22ascending%22%7D%5D%7D%5D%7D | 1 | 0 | 0
Empty Latest Vessel not Complete | 1 | https://helo-frontend-staging-react.azurewebsites.net/containers?viewState=%7B%22queries%22%3A%5B%7B%22queryId%22%3A%22containers_v2%22%2C%22queryName%22%3A%22containers_v2%22%2C%22filters%22%3A%5B%7B%22columnId%22%3A%22vessel%22%2C%22operator%22%3A%22AND%22%2C%22condition%22%3A%22blank%22%2C%22filterValueType%22%3A%22text%22%7D%2C%7B%22columnId%22%3A%22heloItineraryStatus%22%2C%22operator%22%3A%22AND%22%2C%22condition%22%3A%22notContains%22%2C%22filterValue%22%3A%22completed%22%2C%22filterValueType%22%3A%22text%22%7D%5D%7D%5D%7D | 1 | 0 | 0
Dates that should be populated are - Status Date (ETA > 5/1/24) | 0 | https://helo-frontend-staging-react.azurewebsites.net/containers?viewState=%7B%22queries%22%3A%5B%7B%22queryId%22%3A%22containers_v2%22%2C%22queryName%22%3A%22containers_v2%22%2C%22filters%22%3A%5B%7B%22columnId%22%3A%22statusDate%22%2C%22operator%22%3A%22AND%22%2C%22condition%22%3A%22blank%22%2C%22filterValueType%22%3A%22date%22%7D%2C%7B%22columnId%22%3A%22etaShipmentDestination%22%2C%22operator%22%3A%22OR%22%2C%22filterValueType%22%3A%22date%22%2C%22operand1%22%3A%7B%22condition%22%3A%22blank%22%2C%22filterValueType%22%3A%22date%22%7D%2C%22operand2%22%3A%7B%22condition%22%3A%22greaterThan%22%2C%22filterValue%22%3A%222024-05-01+00%3A00%3A00%22%2C%22filterValueType%22%3A%22date%22%7D%7D%5D%2C%22sort%22%3A%5B%7B%22columnId%22%3A%22etaShipmentDestination%22%2C%22sortDirection%22%3A%22ascending%22%7D%5D%7D%5D%7D | 0 | 0 | 0
Shipments | - | - | - | - | -
Sort by Status - no null values - investigate potential issues | 1 | https://helo-frontend-staging-react.azurewebsites.net/shipments?viewState=%7B%22queries%22%3A%5B%7B%22queryId%22%3A%22shipments_v2%22%2C%22queryName%22%3A%22shipments_v2%22%2C%22filters%22%3A%5B%7B%22columnId%22%3A%22status%22%2C%22operator%22%3A%22AND%22%2C%22condition%22%3A%22blank%22%2C%22filterValueType%22%3A%22text%22%7D%5D%7D%5D%7D | 1 | 0 | 0
Status Date - No Null Values | 1 | https://helo-frontend-staging-react.azurewebsites.net/shipments?viewState=%7B%22queries%22%3A%5B%7B%22queryId%22%3A%22shipments_v2%22%2C%22queryName%22%3A%22shipments_v2%22%2C%22filters%22%3A%5B%7B%22columnId%22%3A%22statusDateTime%22%2C%22operator%22%3A%22AND%22%2C%22condition%22%3A%22blank%22%2C%22filterValueType%22%3A%22date%22%7D%5D%7D%5D%7D | 1 | 0 | 0
Empty Origin | 1 | https://helo-frontend-staging-react.azurewebsites.net/shipments?viewState=%7B%22queries%22%3A%5B%7B%22queryId%22%3A%22shipments_v2%22%2C%22queryName%22%3A%22shipments_v2%22%2C%22filters%22%3A%5B%7B%22columnId%22%3A%22shipmentOrigin%22%2C%22operator%22%3A%22AND%22%2C%22condition%22%3A%22blank%22%2C%22filterValueType%22%3A%22text%22%7D%5D%7D%5D%7D | 1 | 0 | 0
Empty Unlading (Destination Port) | 1 | https://helo-frontend-staging-react.azurewebsites.net/shipments?viewState=%7B%22queries%22%3A%5B%7B%22queryId%22%3A%22shipments_v2%22%2C%22queryName%22%3A%22shipments_v2%22%2C%22filters%22%3A%5B%7B%22columnId%22%3A%22destinationPort%22%2C%22operator%22%3A%22AND%22%2C%22condition%22%3A%22blank%22%2C%22filterValueType%22%3A%22text%22%7D%5D%7D%5D%7D | 1 | 0 | 0
Empty BL Destination (Destination) | 1 | https://helo-frontend-staging-react.azurewebsites.net/shipments?viewState=%7B%22queries%22%3A%5B%7B%22queryId%22%3A%22shipments_v2%22%2C%22queryName%22%3A%22shipments_v2%22%2C%22filters%22%3A%5B%7B%22columnId%22%3A%22shipmentDestination%22%2C%22operator%22%3A%22AND%22%2C%22condition%22%3A%22blank%22%2C%22filterValueType%22%3A%22text%22%7D%5D%7D%5D%7D | 1 | 0 | 0
Empty Carrier | 3 | https://helo-frontend-staging-react.azurewebsites.net/shipments?viewState=%7B%22queries%22%3A%5B%7B%22queryId%22%3A%22shipments_v2%22%2C%22queryName%22%3A%22shipments_v2%22%2C%22filters%22%3A%5B%7B%22columnId%22%3A%22carrier%22%2C%22operator%22%3A%22AND%22%2C%22condition%22%3A%22blank%22%2C%22filterValueType%22%3A%22text%22%7D%5D%7D%5D%7D | 3 | 0 | 0
-
Helo Error Stats |  | -
HTTP Operations Dashboard |  | -
Unique Payload errors today |  | -
Helo errors today last 17 hours |  | -
OpenpostMasterBillNumber Errors |  | -
OpengetTrackinginfoByMasterBillNumber Errors |  | -
PortGetBillofLadingBookmark Errors |  | -
PortCreateBillofLadingBookmarkWithBillof LadingNumber Errors |  | -
PortCreateBillofLadingBookmarkWithBillof LadingNumber Errors |  | -
DHLAPIGETrackingInfoByHouseBillNumber Errors |  | -
-
Number of HTTP Operation since yesterday |  | -
Errors logged since yesterday |  | -
Errors logged today |  | -
Errors logged since yesterday Open Track |  | -
Errors logged since yesterday DHL |  | -
Errors logged since yesterday Port Cast |  | -
-
Errors logged since yesterday % |  | -
Errors logged today % |  | -
Errors logged since yesterday Open Track % |  | -
Errors logged since yesterday DHL % |  | -
Errors logged since yesterday Port Cast % |  | -

## Status
Scenarios | STATUS HELO1 | STATUS HELO2
Blank Itinerary Status Containers | Status - Blank | Status - Blank
Blank Latest Vessel (On Water or on Vessel) | Vessel - Blank - On Water or | On Water
| On Vessel | On Vessel
Blank PTA Unlading Port (On Water or On Vessel) | PTA Port of Unlading - Blank - On Water or | On Water
| On Vessel | On Vessel
Blank Last Free Day, Discharged and later | Free Time Expires | Last Free Day
Blank Last Free Day, Discharged and Not Delivered | Free Time Expires | Last Free Day
AND - Not Delivered
Blank PTA Delivery Location | PTA Delivery Location - Blank | ?
Blank Arrival Shipment Destination |  | Arrival Shipment Destination
Containers
Days in Status > 50 (not complete) | Status - Not Completed | Days in status > 50
Not Completed
At Origin Port > 10 days | At Origin Port | At Origin Port
On Water > 15 days | On Water | On Water
At Transshipment Port > 7 days | At Transshipment Port | At Transshipment Port
At Port of Unlading > 5 days | At Port of Unlading | At Port of Unlading
At Port of Unlading > 15 days | At Port of Unlading
Arrived and Available > 5 days | Arrived and Available | Arrived and Available
At Final Destination > 20 days | At Final Destination | At Final Destination
Container Ready Empty > 15 days | Container Ready Empty | Container Ready Empty
Empty Shipment Origin | Origin Port - Blank | Shipment Origin - Blank
Empty Port of Unlading, | Port of Unlading - Blank | Unlading Port - Blank
Empty BL Destination | BL Destination - Blank | ?
Empty Container Delivery Location | Container Delivery Location - Blank | Shipment Destination - Blank
Empty Carrier | Carrier - Blank | Carrier - Blank
Empty Latest Vessel not Complete | Vessel - Not Completed - Blank | Latest Vessel
Not Completed
Dates that should be populated are - Status Date | Status Date - Blank | Status Date - Blank
Shipments
Sort by Status - no null values - investigate potential issues | Status - Blank | Status - Blank
Last Status Date/Time - No Null Values | Last Status Date/Time - Blank | Status Date - Blank
Empty Origin | Origin - Blank | Origin - Blank
Empty Unlading | Unlading - Blank | Destination Port - Blank
Empty BL Destination | BL Destination - Blank | Destination - Blank
Empty Carrier | Carrier - Blank | Carrier - Blank

## Smoke Test Scenarios (hidden)
Scenarios | Link |  | 45008 | 3/23 Comments | 45009 | 3/24 Comments | 45012 | 3/27 Comments | 45013 | 3/28 Comments | 45014 | 3/29 Comments | Last Updated Dif | Bug Link | 45015 | 3/30 Comments | 45016 | 3/31 Comments | 45019 | 4/3 Comments | 45020 | 4/4 Comments | 45027 | 4/11 Comments | 45028 | 4/12 Comments | 45029 | 4/13 Comments | 45030 | 4/14 Comments | 45033 | 4/17 Comments | 45034 | 18-Apr Comments | 18-Apr Comments | 45035 | 19-Apr Comments | 45036 | 20-Apr Comments
Containers without Status | https://helo-frontend-prod.azurewebsites.net/containers?filter=%7B%22itineraryState%22:%7B%22filterType%22:%22text%22,%22type%22:%22blank%22%7D%7D | stuff | 8 |  | 3 |  | 2 |  | 0 |  | 0 |  | -5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0
Blank Vessel (One vessel or on Water only) | https://helo-frontend-prod.azurewebsites.net/containers?filter=%7B%22vessel%22:%7B%22filterType%22:%22text%22,%22type%22:%22blank%22%7D,%22itineraryState%22:%7B%22filterType%22:%22text%22,%22operator%22:%22OR%22,%22condition1%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%22water%22%7D,%22condition2%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%22vessel%22%7D%7D%7D&sorting=%5B%7B%22sort%22:%22asc%22,%22colId%22:%22itineraryState%22%7D%5D |  | 51 |  | 36 | with itinerary | 28 | -8 | 35 |  | 4 | Defect# - 4 vessels on water are missing vessel names | -15 |  | 0 | None of the missing entries are on water | 0 |  | 0 |  | 14 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0
PTA Port of Unlading (Sort by Itenerary state and look for containers on Water) Defect# 4855 | https://helo-frontend-prod.azurewebsites.net/containers?sorting=%5B%7B%22sort%22:%22asc%22,%22colId%22:%22vessel%22%7D%5D&filter=%7B%22portOfUnladingPta%22:%7B%22dateFrom%22:null,%22dateTo%22:null,%22filterType%22:%22date%22,%22type%22:%22blank%22%7D,%22itineraryState%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%22On%20Water%22%7D%7D |  | 217 |  | 210 | 0 with water/vessel true | 210/0 | 210 Containers without PTA Unlading but 0 are on water or on vessel | 7 | all on water and on vessel | 0 |  | -7 |  | 4 |  | 0 |  | 0 |  | 11 |  | 0 |  | 0 |  | 0 |  | 3 | 3 vessels on water on Apr13 | 3 | All 3 are AXEL MAERSK, 1 container on AXEL MAERSK has PTA | 3 |  |  |  |  | 0
Free Time Expires(look at only those containers which are currently at port of unlading - Arrived and Available) | https://helo-frontend-prod.azurewebsites.net/containers?sorting=%5B%7B%22sort%22:%22asc%22,%22colId%22:%22etaPtaDifference%22%7D%5D&filter=%7B%22freeTimeExpires%22:%7B%22dateFrom%22:null,%22dateTo%22:null,%22filterType%22:%22date%22,%22type%22:%22blank%22%7D,%22itineraryState%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%22arrived%22%7D%7D |  | 290 |  | 286 | 185 y, 183 t, diff of 2 |  |  | 308 total, 184 real | 172 complete, 11 at final dest, 0 picked up for delivery, 1 at port of unlading | 1 | Container FANU3102975 has arrived on 3/28 at 2:45 PM local time and probably FTX hasn't been queried/available yet. By the time we get FTX container might have moved on | -4 | https://dev.azure.com/teamsi/The%20Helo%20Project/_workitems/edit/4781 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0
PTA Delivery Location Defects# 4813 | https://helo-frontend-prod.azurewebsites.net/containers?sorting=%5B%7B%22sort%22:%22asc%22,%22colId%22:%22vessel%22%7D%5D&filter=%7B%22ptaDeliveryLocation%22:%7B%22dateFrom%22:null,%22dateTo%22:null,%22filterType%22:%22date%22,%22type%22:%22blank%22%7D%7D |  | 49 | Defect# - Contatiner at Final Destination come in with no history and no PTA | 4 | NY - Sumner routes only | 92 | 92 Containers without PTA delivery location. Defect = 4813 | 7 | Routes: NY - Sumner, Baltimore - Sumner |  | 7 are from Baltimore/NY ->Sumner | -45 | These have been updated from DHL and should now have PTA, Sachin/Kevin | 5 | 1 NY-Sumner, 4 Baltimore->Sumner | 4 | Baltimore->Sumner | 4 | Baltimore->Sumner | 6 | Baltimore->Sumner (4), NY-Sumner (2) | 5 | Baltimore->Sumner (4), NY-Sumner (1) | 10 | Baltimore->Sumner (4), NY-Sumner (6) | 6 | Baltimore->Sumner (4), NY-Sumner (2) | 6 | Baltimore->Sumner (4), NY-Sumner (2) | 6 | (4) Baltimore - Sumner, (2) New York Sumner | 6 |  |  |  |  | 3 | Unlading: 1 NY, 2 Baltimore; BL Dest is Sumner on all 3
Dashboards
Transshipments
Verify that Transshipment metrics match listview counts | [18 empty] | PASSED |  | PASSED |  | PASSED |  | PASSED |  | PASSED |  | PASSED |  | PASSED |  | PASSED |  |  |  |  | PASSED
All widgets render successfully |  |  | PASSED |  | PASSED |  | PASSED |  |  |  | PASSED |  | No change |  | PASSED | PASSED |  |  | PASSED |  | PASSED |  | PASSED |  | PASSED |  | PASSED |  | PASSED |  | PASSED |  | PASSED |  |  |  |  | PASSED
Missing data in list view? |  |  | FAILED | 3 Containers missing Vessel All Containers missing ETA Delivery Location | PASSED | 3 containers missing | FAILED | 2 missing Latest Transshipment Port values (This defect is still open but the manual query should have u pdated all the values) |  |  | PASSED |  |  |  | PASSED | PASSED |  |  | PASSED |  | PASSED |  | PASSED |  | PASSED |  | PASSED |  | PASSED |  | PASSED |  | PASSED |  |  |  |  | PASSED
List view count = Containers at Transshipment Port (current) count | https://helo-frontend-prod.azurewebsites.net/containers?filter=%7B%22itineraryState%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%22trans%22%7D%7D |  | FAILED | Listview Count=10 Top Chart Count (Current)=13 | PASSED | Count = 12, List View = 9 | PASSED | 13/13 |  |  | PASSED |  | No change | https://dev.azure.com/teamsi/The%20Helo%20Project/_workitems/edit/4788 | PASSED | PASSED |  |  | PASSED |  | PASSED |  | PASSED |  | PASSED |  | PASSED |  | PASSED |  | PASSED |  | PASSED |  |  |  |  | PASSED
Carrier Performance
All widgets render successfully |  |  | PASSED |  | PASSED |  | PASSED |  |  |  | PASSED |  | No change |  | PASSED | PASSED |  |  | PASSED |  | PASSED |  | PASSED |  | PASSED |  | PASSED |  | PASSED |  | PASSED |  | PASSED |  |  |  |  | PASSED
Missing data in list view? |  |  | PASSED |  | PASSED |  | PASSED |  |  |  | PASSED |  | No change |  | PASSED | PASSED |  |  | PASSED |  | PASSED |  | PASSED |  | PASSED |  | PASSED |  | PASSED |  | PASSED |  | PASSED |  |  |  |  | PASSED
List view count = Containers Analyzed count |  |  | FAILED | 189 v/s 161 | PASSED |  | FAILED | Containers Analyzed=166/ List View=162 |  |  | PASSED |  | Fixed | https://dev.azure.com/teamsi/The%20Helo%20Project/_workitems/edit/4699 | PASSED | PASSED |  |  | PASSED |  | PASSED |  | PASSED |  | PASSED |  | PASSED |  | PASSED |  | PASSED |  | PASSED |  |  |  |  | PASSED
List Views
Containers
Daily REI smoke test for container list - state X dwell.xlsx
Days in Status > 12 (not in water) | https://helo-frontend-prod.azurewebsites.net/containers?filter=%7B%22daysInCrtState%22:%7B%22filterType%22:%22number%22,%22type%22:%22greaterThan%22,%22filter%22:12%7D,%22itineraryState%22:%7B%22filterType%22:%22text%22,%22operator%22:%22AND%22,%22condition1%22:%7B%22filterType%22:%22text%22,%22type%22:%22notContains%22,%22filter%22:%22Complete%22%7D,%22condition2%22:%7B%22filterType%22:%22text%22,%22type%22:%22notContains%22,%22filter%22:%22Water%22%7D%7D%7D | [29 empty] | 100 | Out of 413 containers (~80ish containers that don't meet this criteria) | 105 |  |  |  |  | 16 | Down, but still need to validate these big ones
Sort by Days in Status (descending) - investigate potential issues of missing event updates... | [12 empty] | 0 | [24 empty] | Pending
At Origin Port > 5 days | https://helo-frontend-prod.azurewebsites.net/containers?filter=%7B%22itineraryState%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%22origin%22%7D,%22daysInCrtState%22:%7B%22filterType%22:%22number%22,%22type%22:%22greaterThan%22,%22filter%22:5%7D%7D |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0
On Vessel > 2 days | https://helo-frontend-prod.azurewebsites.net/containers?filter=%7B%22itineraryState%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%22vessel%22%7D,%22daysInCrtState%22:%7B%22filterType%22:%22number%22,%22type%22:%22greaterThan%22,%22filter%22:2%7D%7D |  | 13 |  | 11 |  | 9 |  | 14 |  | 11 (-3) |  | -2 |  | 13 | 13 |  |  | 20 |  | 27 |  | 13 |  | 13 |  | 13 |  | 16 |  | 16 |  | 16 |  |  |  |  | 8
On Water > 15 days | https://helo-frontend-prod.azurewebsites.net/containers?sorting=%5B%7B%22sort%22:%22asc%22,%22colId%22:%22itineraryState%22%7D%5D&filter=%7B%22itineraryState%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%22water%22%7D,%22daysInCrtState%22:%7B%22filterType%22:%22number%22,%22type%22:%22greaterThan%22,%22filter%22:15%7D%7D |  | 25 |  | 32 |  | 33 |  | 33 |  | 32 (-1) |  | 7 |  | 29 | 26(-3) |  |  | 22 |  | 28 |  | 31 |  | 36 |  | 40 |  | 45 |  | 53 |  | 55 |  | 5107 |  |  | 38
At Transshipment Port > 5 days | https://helo-frontend-prod.azurewebsites.net/containers?sorting=%5B%7B%22sort%22:%22asc%22,%22colId%22:%22itineraryState%22%7D%5D&filter=%7B%22itineraryState%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%22trans%22%7D,%22daysInCrtState%22:%7B%22filterType%22:%22number%22,%22type%22:%22greaterThan%22,%22filter%22:5%7D%7D |  | 1 |  | 5 |  | 7 |  | 7 |  | 7 |  | 4 |  | 7 | 11(+4) |  |  | 5 |  | 8 |  | 13 |  | 16 |  | 10 |  | 10 |  | 18 |  | 18 |  |  |  |  | 4
At Transshipment Port > 7 days | [37 empty] | 4
On Vessel > 5 days | https://helo-frontend-prod.azurewebsites.net/containers?sorting=%5B%7B%22sort%22:%22asc%22,%22colId%22:%22itineraryState%22%7D%5D&filter=%7B%22itineraryState%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%22vessel%22%7D,%22daysInCrtState%22:%7B%22filterType%22:%22number%22,%22type%22:%22greaterThan%22,%22filter%22:5%7D%7D |  | 11 |  | 11 |  | 9 |  | 11 |  | 8(-3) |  | 0 |  | 8 | 10(+2) |  |  | 13 |  | 21 |  | 13 |  | 13 |  | 13 |  | 13 |  | 16 | Some MSC containers greater than or equa to 20+ days old On Vessel, 46 day old container erroring out on API call, open track says container is FULL OUTGATED | 16 |  |  |  |  | 8
On Water > 12 days | https://helo-frontend-prod.azurewebsites.net/containers?sorting=%5B%7B%22sort%22:%22asc%22,%22colId%22:%22itineraryState%22%7D%5D&filter=%7B%22itineraryState%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%22water%22%7D,%22daysInCrtState%22:%7B%22filterType%22:%22number%22,%22type%22:%22greaterThan%22,%22filter%22:12%7D%7D |  | 33 |  | 37 |  | 37 |  | 36 |  | 34(-2) |  | 4 |  | 32 | 33(+1) |  |  | 40 |  | 46 |  | 49 |  | 51 |  | 50 |  | 53 |  | 65 |  | 78 |  | 5107 |  |  | 41 | Down, but still need to validate the big ones
Berthed At Port of Unlading > 1 day | https://helo-frontend-prod.azurewebsites.net/containers?sorting=%5B%7B%22sort%22:%22asc%22,%22colId%22:%22itineraryState%22%7D%5D&filter=%7B%22itineraryState%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%22Berthed%22%7D%7D |  | 0 |  | 4 |  | 2 |  | 0 |  | 1 (+1) |  | 4 |  | 1 | 4(+3) |  |  | 6 |  | 6 |  | 0 |  |  |  | 3 |  | 3 |  | 3 |  | 3 |  |  |  |  | 2
At Port of Unlading > 5 days | https://helo-frontend-prod.azurewebsites.net/containers?sorting=%5B%7B%22sort%22:%22asc%22,%22colId%22:%22itineraryState%22%7D%5D&filter=%7B%22itineraryState%22:%7B%22filterType%22:%22text%22,%22type%22:%22equals%22,%22filter%22:%22At%20port%20of%20unlading%22%7D,%22daysInCrtState%22:%7B%22filterType%22:%22number%22,%22type%22:%22greaterThan%22,%22filter%22:5%7D%7D |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  |  | 0 |  | 0 |  | 1 |  |  |  | 0 |  | 0 |  | 0 |  | 3 |  |  |  |  | 0
On Rail > 5 days | https://helo-frontend-prod.azurewebsites.net/containers?sorting=%5B%7B%22sort%22:%22asc%22,%22colId%22:%22itineraryState%22%7D%5D&filter=%7B%22itineraryState%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%22rail%22%7D,%22daysInCrtState%22:%7B%22filterType%22:%22number%22,%22type%22:%22greaterThan%22,%22filter%22:5%7D%7D |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0
Arrived and Available > 5 days | https://helo-frontend-prod.azurewebsites.net/containers?sorting=%5B%7B%22sort%22:%22asc%22,%22colId%22:%22itineraryState%22%7D%5D&filter=%7B%22itineraryState%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%22arrived%22%7D,%22daysInCrtState%22:%7B%22filterType%22:%22number%22,%22type%22:%22greaterThan%22,%22filter%22:5%7D%7D |  | 0 |  | 0 |  | 1 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  |  | 0 |  | 2 |  | 2 | MAGU5409779 - Picked up 4/10 TCLU6467900 - Discharged 3/30 |  | MAGU5409779 - Picked up 4/10 TCLU6467900 - Discharged 3/30 | 4 | MAGU5409779 - Picked up 4/10 TCLU6467900 - Discharged 3/30 | 1 | MAGU5409779 - Picked up 4/10 TCLU6467900 - Discharged 3/30 | 8 |  | 8 |  |  |  |  | 0
Picked Up for Delivery > 2 days | https://helo-frontend-prod.azurewebsites.net/containers?sorting=%5B%7B%22sort%22:%22asc%22,%22colId%22:%22itineraryState%22%7D%5D&filter=%7B%22itineraryState%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%22Picked%20Up%20for%20Delivery%22%7D,%22daysInCrtState%22:%7B%22filterType%22:%22number%22,%22type%22:%22greaterThan%22,%22filter%22:5%7D%7D |  | 4 |  | 9 |  | 0 |  | 0 |  | 0 |  | 5 |  | 0 | 0 |  |  | 0 |  | 0 |  | 3 |  |  |  | 1 |  | 1 |  | 3 |  | 9 |  | 5107 |  |  | 7
At Final Destination > 5 days | https://helo-frontend-prod.azurewebsites.net/containers?sorting=%5B%7B%22sort%22:%22asc%22,%22colId%22:%22itineraryState%22%7D%5D&filter=%7B%22itineraryState%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%22At%20Final%20Destination%22%7D,%22daysInCrtState%22:%7B%22filterType%22:%22number%22,%22type%22:%22greaterThan%22,%22filter%22:5%7D%7D |  | 63 |  | 58 |  | 17 |  | 24 |  | 24 |  | -5 |  | 25 | 16(-9) |  |  | 17 |  | 17 |  | 24 |  |  |  | 21 |  | 22 |  | 28 |  | 30 |  | 5107 |  |  | 16
Container Ready Empty > 5 days | https://helo-frontend-prod.azurewebsites.net/containers?sorting=%5B%7B%22sort%22:%22asc%22,%22colId%22:%22itineraryState%22%7D%5D&filter=%7B%22itineraryState%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%22Container%20Ready%20Empty%22%7D,%22daysInCrtState%22:%7B%22filterType%22:%22number%22,%22type%22:%22greaterThan%22,%22filter%22:5%7D%7D |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0
Empty Picked Up > 5 days | https://helo-frontend-prod.azurewebsites.net/containers?sorting=%5B%7B%22sort%22:%22asc%22,%22colId%22:%22itineraryState%22%7D%5D&filter=%7B%22itineraryState%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%22Empty%20Picked%20Up%22%7D,%22daysInCrtState%22:%7B%22filterType%22:%22number%22,%22type%22:%22greaterThan%22,%22filter%22:5%7D%7D |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0
Complete (TBD) | [37 empty] | 0
Empty Origin | https://helo-frontend-prod.azurewebsites.net/containers?sorting=%5B%7B%22sort%22:%22asc%22,%22colId%22:%22itineraryState%22%7D%5D&filter=%7B%22originPortOfLading%22:%7B%22filterType%22:%22text%22,%22type%22:%22blank%22%7D%7D |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | No change |  | 0 | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0
Empty Port of Unlading, | https://helo-frontend-prod.azurewebsites.net/containers?sorting=%5B%7B%22sort%22:%22asc%22,%22colId%22:%22itineraryState%22%7D%5D&filter=%7B%22portOfUnlading%22:%7B%22filterType%22:%22text%22,%22type%22:%22blank%22%7D%7D |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | No change |  | 0 | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0
Empty BL Destination | https://helo-frontend-prod.azurewebsites.net/containers?sorting=%5B%7B%22sort%22:%22asc%22,%22colId%22:%22itineraryState%22%7D%5D&filter=%7B%22billOfLadingDestination%22:%7B%22filterType%22:%22text%22,%22type%22:%22blank%22%7D%7D |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | No change |  | 0 | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0
Empty Container Delivery Location | https://helo-frontend-prod.azurewebsites.net/containers?sorting=%5B%7B%22sort%22:%22asc%22,%22colId%22:%22itineraryState%22%7D%5D&filter=%7B%22containerDeliveryLocation%22:%7B%22filterType%22:%22text%22,%22type%22:%22blank%22%7D%7D |  | 3 | 3 containers with empty delivery loc | 1 |  | 0 |  | 0 |  | 0 |  | -2 |  | 0 | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0
Empty Carrier | https://helo-frontend-prod.azurewebsites.net/containers?sorting=%5B%7B%22sort%22:%22asc%22,%22colId%22:%22itineraryState%22%7D%5D&filter=%7B%22carrier%22:%7B%22filterType%22:%22text%22,%22type%22:%22blank%22%7D%7D |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | No change |  | 0 | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0
Empty Vessel | https://helo-frontend-prod.azurewebsites.net/containers?sorting=%5B%7B%22sort%22:%22asc%22,%22colId%22:%22itineraryState%22%7D%5D&filter=%7B%22vessel%22:%7B%22filterType%22:%22text%22,%22type%22:%22blank%22%7D%7D |  | 51 | 51 Empty vessel | 32 |  | 28 |  | 35 |  |  |  | -19 | Updated ref data. Missing info in Opentrack. | 27 | 27 |  |  | 26 |  | 35 |  | 21 |  |  |  | 26 |  | 22 |  | 22 |  | 22 |  |  |  |  | 23
Dates that should be populated are | https://helo-frontend-prod.azurewebsites.net/containers?sorting=%5B%7B%22sort%22:%22asc%22,%22colId%22:%22itineraryDateTime%22%7D%5D&filter=%7B%22itineraryState%22:%7B%22filterType%22:%22text%22,%22type%22:%22notBlank%22%7D,%22itineraryDateTime%22:%7B%22dateFrom%22:null,%22dateTo%22:null,%22filterType%22:%22date%22,%22type%22:%22blank%22%7D%7D |  | PASSED |  | PASSED |  | PASSED |  | PASSED |  | PASSED |  | No change |  | PASSED | PASSED |  |  | PASSED |  | PASSED |  | PASSED |  |  |  | PASSED |  | PASSED |  | PASSED |  | PASSED |  |  |  |  | PASSED
Container ID drill down works |  |  | PASSED |  | PASSED |  | PASSED |  | PASSED |  | PASSED |  | No change
Shipments
Sort by Status - no null values - investigate potential issues | https://helo-frontend-prod.azurewebsites.net/shipments?sorting=%5B%7B%22sort%22:%22desc%22,%22colId%22:%22itineraryState%22%7D%5D&filter=%7B%22itineraryState%22:%7B%22filterType%22:%22text%22,%22type%22:%22blank%22%7D%7D |  | 8 | 8 with null status | 4 |  | 2 |  | 0 |  | 0 |  | -4 |  | 0 | 0 |  |  | 0 |  | 1(+1) |  | 1 | No Container |  | No Container | 1 | No Container | 1 | No Container | 1 | No container | 1 | HANA32115 has no container, has not had an update since 04-13 |  |  |  | 1 | Shipment without container
Last Status Date/Time - No Null Values | https://helo-frontend-prod.azurewebsites.net/shipments?sorting=%5B%7B%22sort%22:%22desc%22,%22colId%22:%22itineraryState%22%7D%5D&filter=%7B%22itineraryState%22:%7B%22filterType%22:%22text%22,%22type%22:%22notBlank%22%7D,%22itineraryDateTime%22:%7B%22dateFrom%22:null,%22dateTo%22:null,%22filterType%22:%22date%22,%22type%22:%22blank%22%7D%7D |  |  | Passed | 3 |  | 0 |  | 0 |  | 0 |  | 3 |  | 0 | 0 |  |  | 0 |  | 1 |  | 1 |  |  |  | 1 |  | 1 |  | 1 |  | 1 | HANA32115 has no container, has not had an update since 04-13 |  |  |  | 1 | Shipment without container
Empty Origin | https://helo-frontend-prod.azurewebsites.net/shipments?sorting=%5B%7B%22sort%22:%22asc%22,%22colId%22:%22itineraryDateTime%22%7D%5D&filter=%7B%22originPortOfLading%22:%7B%22filterType%22:%22text%22,%22type%22:%22blank%22%7D%7D |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | No change |  | 0 | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0
Empty Unlading | https://helo-frontend-prod.azurewebsites.net/shipments?sorting=%5B%7B%22sort%22:%22asc%22,%22colId%22:%22itineraryDateTime%22%7D%5D&filter=%7B%22portOfUnlading%22:%7B%22filterType%22:%22text%22,%22type%22:%22blank%22%7D%7D |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | No change |  | 0 | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0
Empty BL Destination | https://helo-frontend-prod.azurewebsites.net/shipments?sorting=%5B%7B%22sort%22:%22asc%22,%22colId%22:%22itineraryDateTime%22%7D%5D&filter=%7B%22billOfLadingDestination%22:%7B%22filterType%22:%22text%22,%22type%22:%22blank%22%7D%7D |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | No change |  | 0 | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0
Empty Carrier | https://helo-frontend-prod.azurewebsites.net/shipments?sorting=%5B%7B%22sort%22:%22asc%22,%22colId%22:%22itineraryDateTime%22%7D%5D&filter=%7B%22carrier%22:%7B%22filterType%22:%22text%22,%22type%22:%22blank%22%7D%7D |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | No change |  | 0 | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  |  | 0
Shipment ID drill down works |  |  | PASSED |  | PASSED |  | PASSED |  | PASSED |  | PASSED |  | No change |  | PASSED | PASSED |  |  | PASSED |  | PASSED |  | PASSED |  |  |  | PASSED |  | PASSED |  | PASSED |  | PASSED |  |  |  |  | PASSED
Containers Not Tracked | Compile all ingested csvs and compare against shipment list view
Operations Dashboard
Errors logged since yesterday | https://helo-frontend-prod.azurewebsites.net/http-operations?filter=%7B%22requestData%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%22Rec%22%7D,%22status%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%22Error%22%7D,%22createdDate%22:%7B%22filterType%22:%22text%22,%22operator%22:%22OR%22,%22condition1%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%2204-18%22%7D,%22condition2%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%2204-19%22%7D%7D%7D&sorting=%5B%7B%22sort%22:%22desc%22,%22colId%22:%22createdDate%22%7D%5D | [34 empty] | 3639
Errors logged today | https://helo-frontend-prod.azurewebsites.net/http-operations?filter=%7B%22requestData%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%22Rec%22%7D,%22status%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%22Error%22%7D,%22createdDate%22:%7B%22filterType%22:%22text%22,%22operator%22:%22OR%22,%22condition1%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%2204-19%22%7D,%22condition2%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%2204-19%22%7D%7D%7D&sorting=%5B%7B%22sort%22:%22desc%22,%22colId%22:%22createdDate%22%7D%5D | [34 empty] | 12
Errors logged yesterday-today Open Track | https://helo-frontend-prod.azurewebsites.net/http-operations?filter=%7B%22requestData%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%22Rec%22%7D,%22status%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%22Error%22%7D,%22createdDate%22:%7B%22filterType%22:%22text%22,%22operator%22:%22OR%22,%22condition1%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%2204-19%22%7D,%22condition2%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%2204-18%22%7D%7D,%22operationUri%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%22Open%22%7D%7D&sorting=%5B%7B%22sort%22:%22desc%22,%22colId%22:%22createdDate%22%7D%5D | [34 empty] | 107
Errors logged yesterday-today DHL | https://helo-frontend-prod.azurewebsites.net/http-operations?filter=%7B%22requestData%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%22Rec%22%7D,%22status%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%22Error%22%7D,%22createdDate%22:%7B%22filterType%22:%22text%22,%22operator%22:%22OR%22,%22condition1%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%2204-19%22%7D,%22condition2%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%2204-18%22%7D%7D,%22operationUri%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%22dhl%22%7D%7D&sorting=%5B%7B%22sort%22:%22desc%22,%22colId%22:%22createdDate%22%7D%5D | [34 empty] | 3015
Errors logged yesterday-today Port Cast | https://helo-frontend-prod.azurewebsites.net/http-operations?filter=%7B%22requestData%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%22Rec%22%7D,%22status%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%22Error%22%7D,%22createdDate%22:%7B%22filterType%22:%22text%22,%22operator%22:%22OR%22,%22condition1%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%2204-19%22%7D,%22condition2%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%2204-18%22%7D%7D,%22operationUri%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%22port%22%7D%7D&sorting=%5B%7B%22sort%22:%22desc%22,%22colId%22:%22createdDate%22%7D%5D | [34 empty] | 518
Note on A3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: https://dev.azure.com/teamsi/The%20Helo%20Project/_workitems/edit/4783
Note on E6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Stuff :D
Note on J6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Sachin to enter new defect and assign to Harry
Note on A45: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Drilldown from Shipment ID-Container ID ?

## Sheet4 (hidden)
45008 | 8 | 51 | 217 | 290 | 49 |  | PASSED | FAILED | FAILED | PASSED | PASSED | FAILED |  | 0 | 13 | 25 | 1 | 11 | 33 | 0 | 0 | 0 | 0 | 4 | 63 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 51 | PASSED | PASSED | 8 |  | 0 | 0 | 0 | 0 | PASSED
3/23 Comments |  |  |  |  | Defect# - Contatiner at Final Destination come in with no history and no PTA |  |  | 3 Containers missing Vessel All Containers missing ETA Delivery Location | Listview Count=10 Top Chart Count (Current)=13 |  |  | 189 v/s 161 | [18 empty] | 3 containers with empty delivery loc |  | 51 Empty vessel |  |  | 8 with null status | Passed
45035
3/24 Comments |  | with itinerary | 0 with water/vessel true | 185 y, 183 t, diff of 2 | NY - Sumner routes only |  |  | 3 containers missing | Count = 12, List View = 9
45034 | 0 | 0 | 3 | 0 | 6 | PASSED | PASSED | PASSED | PASSED | PASSED | PASSED | PASSED | 105 | 0 | 16 | 55 | 18 | 16 | 78 | 3 | 3 | 0 | 8 | 9 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | PASSED |  | 1 | 1 | 0 | 0 | 0 | 0 | PASSED
3/27 Comments |  | -8 | 210 Containers without PTA Unlading but 0 are on water or on vessel |  | 92 Containers without PTA delivery location. Defect = 4813 |  |  | 2 missing Latest Transshipment Port values (This defect is still open but the manual query should have u pdated all the values) | 13/13 |  |  | Containers Analyzed=166/ List View=162
45033 | 0 | 0 | 3 | 0 | 6 | PASSED | PASSED | PASSED | PASSED | PASSED | PASSED | PASSED | 100 | 0 | 16 | 53 | 18 | 16 | 65 | 3 | 0 | 0 | 8 | 3 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | PASSED |  | 1 | 1 | 0 | 0 | 0 | 0 | PASSED
3/28 Comments |  |  | all on water and on vessel | 172 complete, 11 at final dest, 0 picked up for delivery, 1 at port of unlading | Routes: NY - Sumner, Baltimore - Sumner
45030 | 0 | 0 | 3 | 0 | 6 | PASSED | PASSED | PASSED | PASSED | PASSED | PASSED | PASSED |  | 0 | 16 | 45 | 10 | 13 | 53 | 3 | 0 | 0 | 1 | 1 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | PASSED |  | 1 | 1 | 0 | 0 | 0 | 0 | PASSED
3/29 Comments |  | Defect# - 4 vessels on water are missing vessel names |  | Container FANU3102975 has arrived on 3/28 at 2:45 PM local time and probably FTX hasn't been queried/available yet. By the time we get FTX container might have moved on | 7 are from Baltimore/NY ->Sumner
45029 | 0 | 0 | 0 | 0 | 6 | PASSED | PASSED | PASSED | PASSED | PASSED | PASSED | PASSED |  | 0 | 13 | 40 | 10 | 13 | 50 | 3 | 0 | 0 | 4 | 1 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | PASSED |  | 1 | 1 | 0 | 0 | 0 | 0 | PASSED
3/30 Comments |  | None of the missing entries are on water |  |  | 1 NY-Sumner, 4 Baltimore->Sumner |  | PASSED | PASSED | PASSED | PASSED | PASSED | PASSED |  | 0 | 13 | 26(-3) | 11(+4) | 10(+2) | 33(+1) | 4(+3) | 0 | 0 | 0 | 0 | 16(-9) |  | 0 | 0 | 0 | 0 | 0 | 0 | 27 | PASSED |  | 0 | 0 | 0 | 0 | 0 | 0 | PASSED
45028 | 0 | 0 | 0 | 0 | 10 | PASSED | PASSED | PASSED | PASSED | PASSED | PASSED | PASSED |  | 0 | 13 | 36 | 16 | 13 | 51
3/31 Comments |  |  |  |  | Baltimore->Sumner
45027 | 0 | 0 | 0 | 0 | 5 | PASSED | PASSED | PASSED | PASSED | PASSED | PASSED | PASSED |  | 0 | 13 | 31 | 13 | 13 | 49 | 0 | 1 | 0 | 2 | 3 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | PASSED |  | 1 | 1 | 0 | 0 | 0 | 0 | PASSED
4/3 Comments |  |  |  |  | Baltimore->Sumner
45020 | 0 | 14 | 11 | 0 | 6 | PASSED | PASSED | PASSED | PASSED | PASSED | PASSED | PASSED |  | 0 | 27 | 28 | 8 | 21 | 46 | 6 | 0 | 0 | 2 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | PASSED |  | 1(+1) | 1 | 0 | 0 | 0 | 0 | PASSED
4/4 Comments |  |  |  |  | Baltimore->Sumner (4), NY-Sumner (2)
45019 | 0 | 0 | 0 | 0 | 4 | PASSED | PASSED | PASSED | PASSED | PASSED | PASSED | PASSED |  | 0 | 20 | 22 | 5 | 13 | 40 | 6 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | PASSED |  | 0 | 0 | 0 | 0 | 0 | 0 | PASSED
4/11 Comments |  |  |  |  | Baltimore->Sumner (4), NY-Sumner (1) | [17 empty] | MAGU5409779 - Picked up 4/10 TCLU6467900 - Discharged 3/30 | [12 empty] | No Container
45016 | 0 | 0 | 0 | 0 | 4
4/12 Comments |  |  |  |  | Baltimore->Sumner (4), NY-Sumner (6) | [17 empty] | MAGU5409779 - Picked up 4/10 TCLU6467900 - Discharged 3/30 | [12 empty] | No Container
45015 | 0 | 0 | 4 | 0 | 5 |  | PASSED | PASSED | PASSED | PASSED | PASSED | PASSED |  | 0 | 13 | 29 | 7 | 8 | 32 | 1 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | PASSED |  | 0 | 0 | 0 | 0 | 0 | 0 | PASSED
4/13 Comments |  |  |  |  | Baltimore->Sumner (4), NY-Sumner (2) | [17 empty] | MAGU5409779 - Picked up 4/10 TCLU6467900 - Discharged 3/30 | [12 empty] | No Container
45014 | 0 | 4 | 0 | 1 |  |  | PASSED | PASSED | PASSED | PASSED | PASSED | PASSED |  | 0 | 11 (-3) | 32 (-1) | 7 | 8(-3) | 34(-2) | 1 (+1) | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | PASSED | PASSED | 0 | 0 | 0 | 0 | 0 | 0 | PASSED
4/14 Comments |  |  | 3 vessels on water on Apr13 |  | Baltimore->Sumner (4), NY-Sumner (2) | [17 empty] | MAGU5409779 - Picked up 4/10 TCLU6467900 - Discharged 3/30 | [12 empty] | No Container
45013 | 0 | 35 | 7 | 308 total, 184 real | 7 | [8 empty] | 0 | 14 | 33 | 7 | 11 | 36 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | PASSED | PASSED | 0 | 0 | 0 | 0 | 0 | 0 | PASSED
4/17 Comments |  |  | All 3 are AXEL MAERSK, 1 container on AXEL MAERSK has PTA |  | (4) Baltimore - Sumner, (2) New York Sumner | [7 empty] | Out of 413 containers (~80ish containers that don't meet this criteria) |  |  |  |  | Some MSC containers greater than or equa to 20+ days old On Vessel, 46 day old container erroring out on API call, open track says container is FULL OUTGATED | [17 empty] | No container
45012 | 2 | 28 | 210/0 |  | 92 |  | PASSED | FAILED | PASSED | PASSED | PASSED | FAILED |  | 0 | 9 | 33 | 7 | 9 | 37 | 2 | 0 | 0 | 1 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | PASSED | PASSED | 2 | 0 | 0 | 0 | 0 | 0 | PASSED
18-Apr Comments | [35 empty] | HANA32115 has no container, has not had an update since 04-13 | HANA32115 has no container, has not had an update since 04-13
18-Apr Comments | [15 empty] | 5107 |  |  | 5107 |  |  |  |  | 5107 | 5107
45009 | 3 | 36 | 210 | 286 | 4 |  | PASSED | PASSED | PASSED | PASSED | PASSED | PASSED |  | 0 | 11 | 32 | 5 | 11 | 37 | 4 | 0 | 0 | 0 | 9 | 58 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 32 | PASSED | PASSED | 4 | 3 | 0 | 0 | 0 | 0 | PASSED
19-Apr Comments
Note on H2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Stuff :D
Note on H7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Sachin to enter new defect and assign to Harry

## Sheet3 (hidden)
Operations Dashboard
Errors logged yesterday | https://helo-frontend-prod.azurewebsites.net/http-operations?filter=%7B%22requestData%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%22Rec%22%7D,%22status%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%22Error%22%7D,%22createdDate%22:%7B%22filterType%22:%22text%22,%22operator%22:%22OR%22,%22condition1%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%2204-18%22%7D,%22condition2%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%2204-19%22%7D%7D%7D&sorting=%5B%7B%22sort%22:%22desc%22,%22colId%22:%22createdDate%22%7D%5D
Errors logged today | https://helo-frontend-prod.azurewebsites.net/http-operations?filter=%7B%22requestData%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%22Rec%22%7D,%22status%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%22Error%22%7D,%22createdDate%22:%7B%22filterType%22:%22text%22,%22operator%22:%22OR%22,%22condition1%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%2204-19%22%7D,%22condition2%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%2204-19%22%7D%7D%7D&sorting=%5B%7B%22sort%22:%22desc%22,%22colId%22:%22createdDate%22%7D%5D
Errors logged yesterday-today Open Track | https://helo-frontend-prod.azurewebsites.net/http-operations?filter=%7B%22requestData%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%22Rec%22%7D,%22status%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%22Error%22%7D,%22createdDate%22:%7B%22filterType%22:%22text%22,%22operator%22:%22OR%22,%22condition1%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%2204-19%22%7D,%22condition2%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%2204-18%22%7D%7D,%22operationUri%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%22Open%22%7D%7D&sorting=%5B%7B%22sort%22:%22desc%22,%22colId%22:%22createdDate%22%7D%5D
Errors logged yesterday-today DHL | https://helo-frontend-prod.azurewebsites.net/http-operations?filter=%7B%22requestData%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%22Rec%22%7D,%22status%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%22Error%22%7D,%22createdDate%22:%7B%22filterType%22:%22text%22,%22operator%22:%22OR%22,%22condition1%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%2204-19%22%7D,%22condition2%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%2204-18%22%7D%7D,%22operationUri%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%22dhl%22%7D%7D&sorting=%5B%7B%22sort%22:%22desc%22,%22colId%22:%22createdDate%22%7D%5D
Errors logged yesterday-today Port Cast | https://helo-frontend-prod.azurewebsites.net/http-operations?filter=%7B%22requestData%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%22Rec%22%7D,%22status%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%22Error%22%7D,%22createdDate%22:%7B%22filterType%22:%22text%22,%22operator%22:%22OR%22,%22condition1%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%2204-19%22%7D,%22condition2%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%2204-18%22%7D%7D,%22operationUri%22:%7B%22filterType%22:%22text%22,%22type%22:%22contains%22,%22filter%22:%22port%22%7D%7D&sorting=%5B%7B%22sort%22:%22desc%22,%22colId%22:%22createdDate%22%7D%5D

## Sheet1 (hidden)
MBL | Carrier | Cont. # | Latest Milestone | Vessel
MEDUZF737957 | MSC | MSCU4642664 | 2/16 Export Loaded on Vessel | MSC DOMNA X Voyage UX306A
MEDUZF737940 | MSC | TCLU4435083 | 2/16 Export Loaded on Vessel | MSC DOMNA X Voyage UX306A
MEDUIE356999 | MSC | DFSU1487495 | 2/17 Full Transshipment Loaded | MSC BEATRICE Voyage QJ306N
MEDUZF734806 | MSC | MSCU5863079 | 2/23 Full Transshipment Loaded | MSC DOMNA X Voyage UX306A
MEDUZF734798 | MSC | MSCU4706985 | 2/23 Full Transshipment Loaded | MSC DOMNA X Voyage UX306A
MEDUIE357005 | MSC | MSDU7515857 | 2/24 Full Transshipment Positioned In | MSC HAILEY ANN III Voyage HW305R
MEDUZF796912 | MSC | TGHU4639888 | 3/16 Import Discharged from Vessel | MSC BEATRICE Voyage 306N
MEDUZF796771 | MSC | MSDU4050000 | 3/16 Import Discharged from Vessel | MSC BEATRICE Voyage 306N
MEDUI0867057 | MSC | MSMU5281822 | 3/3 Full Transshipment Discharged | MSC TRADER II Voyage HA308R
MEDUI0867065 | MSC | TRLU4842494 | 3/3 Full Transshipment Discharged | MSC TRADER II Voyage HA308R
HLCUHA3230101144 | Hapag Lloyd | HLXU8540938 | 2/25 Gate In Empty Phoenix | SEASPAN ADONIS
HLCUSGN221272802 | Hapag Lloyd | TCLU8117326 | 2/22 Gate In Empty Phoenix | ONE EAGLE

## Sheet2 (hidden)
itineraryState | Complete
daysInCrtState | Count of containerNumber
2 | 57
3 | 57
4 | 59
5 | 2
6 | 9
7 | 48
8 | 52
9 | 63
10 | 47
11 | 55
13 | 8
14 | 39
15 | 68
16 | 94
18 | 77
19 | 4
20 | 11
21 | 77
22 | 53
23 | 82
24 | 85
25 | 76
27 | 10
28 | 87
29 | 95
30 | 33
17 | 73
1 | 10
Grand Total | 1431